## Sheet1
# | Description | Priority | Estimate
1 | Module Development | 2
2 | Module Categorization | 1
3 | Type 3, Type 4 and Other page development | 1
4 | Type 1, Type 2 and UDQ development | 1
5 | Common Libraty Enhancements | 2
6 | API Analysis & Development Phase-II | 3
7 | Security Implementation & Integration | 5
8 | MAC Integration | 5
9 | Testing (Functional, Browser based etc.) | 6
10 | Bux Fixes | 6
11 | Type 1, Type 2 and UDQ development

## Sheet2
# | Tasks | Estimates(Days) | Category | Type 1 Screens | Type 2 | UDQ | Type 3 | Type 4 | CRUD/Utility Pages.
I | Infrastructure changes
| Metadata creation | 15 | Analysis | 13 | 9 | 33 | 6 | 1
| Design analysis for additional field types | 1 | Analysis
| Any Common Library Enhancements (Recurring) | 5 | Analysis
II | Remaining UDQ, Type 1 and Type 2
| UI Development | 40 | UI | 13 | 9 | 33
| API Development | 60 | API
| UI & API Integration | 10 | Integration
III | Other/Rest of UIs
| Design for Complex UIs | 5 | Analysis
| Custom UI support along with Re-usable comps | 5 | Integration
| Type 3 UI Development | 15 | UI |  |  |  | 6
| Type 4 UI Development | 5 | UI |  |  |  |  | 1
| UI Pages Development & External links | 5 | UI
| Additional Utilities/CURD Page development | 15 | UI | [5 empty] | 7 Complex Utilities
| API Design & Development | 20 | API
| Utility/CRUD API Development (Backup/Restore/Permissions & more.) | 25 | API
| UI API Integration | 5 | Integration
IV | Security & Integration
| TF Security API Development | 5 | Integration
| Security Services/Infrastructure changes for TF | 5 | Integration
| MAC/Module Integration | 5 | Integration
| Lab Deployment | 3 | Deployment
V | QA Testing
| Functional/Manual Testing |  | Testing
| Automation Testing |  | Testing
| Browser (Chrome/FF/Edge/Ipad) Based Testing |  | Testing
VI | Bug Fixes |  | Testing
| Total | 249