## Slide 1: Analysis – Optimization/Effort Reduction
TF Web Application – New Architecture

## Slide 2: Option 1
Replicate Functionality as-is.
No Design changes
All UI/Services implemented as currently designed using React/Redux & Spring MVC
Estimated Effort - ~6000 hrs.
Estimated Completion Date – 4/6/2021

## Slide 3: Option 1
Concerns
  TimeLine/Effort
  No optimization/automation opportunities explored.
  Project structure
    Cascading impact of unknowns.
    Positive impact of code reuse not captured/quantified.

## Slide 4: Analysis
Design Changes
  Present all CRUD forms as Modals (from grid pages).
  Present all Lookup grids as Modals (from grid pages).
  Present all child pages (with grids) as modals.
  Eliminate the need for related links.
    Group pages/links together as modules.
      * Requires input from TF team.
  Eliminate recent usage (if possible)
    Constraint - All entities have specific API for recent usage.
  Build reusable pages and grid components per screen type*
    Side effect – increases API complexity.
  Potentially reuse filter components. (generic filters)
    Use grid filters to reduce filter complexity.
  Potentially use a form builder to build simple CURD screens.
    Side effect – increases API complexity.

## Slide 5: Analysis
Design/Implementation - Optimization opportunities
  Type 1 Screens (#15 areas)
    Have a single grid and form(s) for Create/Update/Deletion of a single entity.
    Grid complexity ranges from Low to Medium (based on # columns)
    CRUD complexity ranges from Low to Complex (2 fields to 58 fields)
    Design/Implementation Approach
      Create components to reuse the following
        Read only Grid with a link to CRUD form(s)
        Build support for multiple data loading endpoints/APIs.
        Build support for CRUD operations based on entity types.

## Slide 6: Analysis
Design/Implementation - Optimization opportunities
  Type 2 Screens (#11 areas)
    Lookup parent entity first & have a single grid and form(s) for Create/Update/Deletion of a single entity.
    Grid complexity ranges from Low to Medium (based on # columns)
    CRUD complexity ranges from Low to Complex (4 fields to 20 fields)
    Design/Implementation Approach
      Create components to reuse the following
        Modal to pick parent entity.
        Read only Grid with a link to CRUD form(s)
        Build support for multiple data loading endpoints/APIs for
          Lookup parent entity grids.
          Child entity grids.
        Build support for CRUD operations based on entity types.

## Slide 7: Analysis
Design/Implementation - Optimization opportunities
  User Data Queries (reporting) (#34 reports)
    Eliminate filters where applicable. (use JQ grid filters)
    Use common read-only grid component.
    Common page with filters/without filters.
      Impacts API complexity.
    Use common filter components/lookups.
    Design/Implementation Approach
      Create components to reuse the following
        Modal for filters.
        Read only Grid with filters to load data based on grid metadata.

## Slide 8: Analysis
Design/Implementation - Optimization opportunities
  All other pages/areas
    Potential re-use of read-only grids.
    Potential res-use of filter/lookup components

## Slide 9: Option 2
Estimated effort reduction approx. 25-30%
  Focus on code reuse/automation.
  Build project infrastructure first.
  Break application into modules based on related functionality.
    Deliver to product team as and when done with each module.
    Do certification in parallel.
  Build APIs along with UI (no mock data/stub APIs)
Project Structure (proposed)
  Establish a goal/end date for project.
  Drive towards goal via milestones/phases.
    Use bi-weekly iterations.
  Do JIT planning (project plan) for next milestone/phase.
    First milestone – Infrastructure implementation (UI/API/Security/MAC)
      Includes re-usable UI components/widgets etc.
      Implement one area per screens type with APIs
      Approximate Duration: 6-8 weeks.
    Next Milestones – Implement each module in succession.