## Metadata
Screen Name | Screen Type | Folder Name (\\ntsrv\Common\Strategic Solutions\Designs & Specs\TF New Arch\Metadata-Mockdata\) | Owner/Creator | Has Filter or CRUD | Metadata Complete? | Mockdata Available? | Tested With Harness | Start Date | Completion Date | Peer Review Complete | Dev Complete | QA Complete
User Data Queries_Tax Authority | RO-Type 1-Grid | RG_Tax Authority | Raji | No | Yes | Yes | Yes | 2020-05-18 | 2020-05-21 | 2020-05-21
User Data Queries_Custom Taxes | RO-Type 1-Grid | RG_Custom Taxes | Raji | No | Yes | Yes | Yes | 2020-05-18 | 2020-05-21 | 2020-05-21
User Data Queries_BSI Taxes | RO-Type 1-Grid | RG_BSI Taxes | Raji | No | Yes | Yes | Yes | 2020-05-18 | 2020-05-21 | 2020-05-21
User Data Queries_Tax Types | RO-Type 1-Grid | RG_Tax Types | Raji | No | Yes | Yes | Yes | 2020-05-18 | 2020-05-21 | 2020-05-21
User Data Queries_Employee Groups | RO-Type 1-Grid | RG_Employee Groups | Raji | No | Yes | Yes | Yes | 2020-05-18 | 2020-05-21 | 2020-05-21
User Data Queries_Garnishment Groups | RO-Type 1-Grid | RG_Garnishment Groups | Raji | No | Yes | Yes | Yes | 2020-05-18 | 2020-05-21 | 2020-05-21
User Data Queries_Disposable Overrides | RO-Type 1-Grid | RG_Disposable Overrides | Raji | No | Yes | Yes | Yes | 2020-05-18 | 2020-05-21 | 2020-05-21
User Data Queries_Custom Garnishments | RO-Type 1-Grid | RG_Custom Garnishments | Raji | No | Yes | Yes | Yes | 2020-05-18 | 2020-05-21 | 2020-05-21
User Data Queries_Garnishment Formula Override | RO-Type 1-Grid | RG_Garnishment Formula Override | Raji | No | Yes | Yes | Yes | 2020-05-18 | 2020-05-21 | 2020-05-21
User Data Queries_All Mapped Tax Types | RO-Type 1-Grid | RG_All Mapped Tax Types | Raji | No | Yes | Yes | Yes | 2020-05-18 | 2020-05-21 | 2020-05-21
User Data Queries_All Mapped Tax User Data Queries_Codes | RO-Type 1-Grid | RG_All Mapped Tax RG_Codes | Raji | No | Yes | Yes | Yes | 2020-05-18 | 2020-05-21 | 2020-05-21
User Data Queries_All Mapped Pay User Data Queries_Codes | RO-Type 1-Grid | RG_All Mapped Pay RG_Codes | Raji | No | Yes | Yes | Yes | 2020-05-18 | 2020-05-21 | 2020-05-21
User Data Queries_Companies | RO-Type 1-Grid | RG_Companies | Raji | No | Yes | Yes | Yes | 2020-05-18 | 2020-05-21 | 2020-05-21
User Data Queries_Experience Rates | RO-Type 1-Grid | RG_ExperienRG_Ce Rates | Vinit | No | Yes | Yes | Yes | 2020-05-18 | 2020-05-21 | 2020-05-21
User Data Queries_Supplemental Methods | RO-Type 1-Grid | RG_Supplemental Methods | Raji | No | Yes | Yes | Yes | 2020-05-18 | 2020-05-21 | 2020-05-21
User Data Queries_Marital Status | RO-Type 1-Grid | RG_Marital Status | Raji | Yes | Yes | Yes | Yes | 2020-05-18 | 2020-05-21 | 2020-05-21
User Data Queries_Resident/Work Validation | RO-Type 1-Grid | RG_Resident/Work Validation | Raji | Yes | Yes | Yes | Yes | 2020-05-18 | 2020-05-21 | 2020-05-21
User Data Queries_Unemployment | RO-Type 1-Grid | RG_Unemployment | Raji | Yes | Yes | Yes | Yes | 2020-05-18 | 2020-05-21 | 2020-05-21
User Data Queries_Populated V3 States | RO-Type 1-Grid | Populated V3 States | Vinit | Yes | Yes | Yes | Yes | 2020-05-18 | 2020-05-21 | 2020-05-22
User Data Queries_Monthly/Quarterly Tax Type | RO-Type 1-Grid | RG_Monthly/Quarterly Tax Type | Raji | Yes | Yes | Yes | Yes | 2020-05-18 | 2020-05-21 | 2020-05-22
User Data Queries_Taxability for Authority | RO-Type 1-Grid | RG_Taxability for Authority | Raji | Yes | Yes | Yes | Yes | 2020-05-18 | 2020-05-21 | 2020-05-21
User Data Queries_Custom Taxability for Authority | RO-Type 1-Grid | RG_Custom Taxability for Authority | Raji | Yes | Yes | Yes | Yes | 2020-05-18 | 2020-05-21 | 2020-05-22
User Data Queries_Custom Overrides for Authority | RO-Type 1-Grid | RG_Custom Overrides for Authority | Raji | Yes | Yes | Yes | Yes | 2020-05-18 | 2020-05-21 | 2020-05-21
User Data Queries_Custom Garnishment Formula | RO-Type 1-Grid | RG_Custom Garnishment Formula | Raji | Yes | Yes | Yes | Yes | 2020-05-18 | 2020-05-21 | 2020-05-21
User Data Queries_All BSI Plans | RO-Type 1-Grid | RG_All BSI Plans | Raji | No | Yes | Yes | Yes | 2020-05-18 | 2020-05-21 | 2020-05-22
User Data Queries_Garnishments Requiring Filing Status | RO-Type 1-Grid | RG_Garnishments Requiring Filing Status | Raji | Yes | Yes | Yes | Yes | 2020-05-18 | 2020-05-21 | 2020-05-22
User Data Queries_Ordered-PerCent Garnishments | RO-Type 1-Grid | RG_Ordered-PerCent Garnishments | Raji | Yes | Yes | Yes | Yes | 2020-05-18 | 2020-05-21 | 2020-05-22
User Data Queries_Valid Tax Formulas | RO-Type 1-Grid | RG_Valid Tax Formulas | Raji | Yes | Yes | Yes | Yes | 2020-05-18 | 2020-05-21 | 2020-05-22
User Data Queries_All Mapped Tax Codes With County | RO-Type 1-Grid | RG_All Mapped Tax Codes With County | Raji | No | Yes | Yes | Yes | 2020-05-18 | 2020-05-21 | 2020-05-22
User Data Queries_Wage Limits By Authority And Tax Type | RO-Type 1-Grid | RG_Wage Limits By Authority And Tax Type | Raji | Yes | Yes | Yes | Yes | 2020-05-18 | 2020-05-21 | 2020-05-21
User Data Queries_Garnishment Disposable Wages | RO-Type 1-Grid | RG_Garnishment Disposable Wages | Raji | Yes | Yes | Yes | Yes | 2020-05-18 | 2020-05-21 | 2020-05-22
User Data Queries_Statement of Exemption Authorities | RO-Type 1-Grid | RG_Statement of Exemption Authorities | Raji | No | Yes | Yes | Yes | 2020-05-18 | 2020-05-21 | 2020-05-22
User Data Queries_Minimum Age Taxes | RO-Type 1-Grid | RG_Minimum Age Taxes | Raji | Yes | Yes | Yes | Yes | 2020-05-18 | 2020-05-21 | 2020-05-22
User Data Queries_Garnishment Parameters | RO-Type 1-Grid | RG_Garnishment Parameters | Raji | Yes | Yes | Yes | Yes | 2020-05-18 | 2020-05-21 | 2020-05-22
Populated V3 States | RO-Type 1-Grid |  |  | No | Yes | Yes | Yes
Address Overrides-Fields | RO-Type 1-Grid |  | Raji | Yes | Yes
Address Overrides-Page | RO-Type 1-Grid |  | Raji | Yes | Yes
All BSI Plans | RO-Type 1-Grid |  |  | No | Yes
All Mapped Tax Codes With County | RO-Type 1-Grid |  |  | No | Yes
Statement of Exemption Authorities | RO-Type 1-Grid |  |  | No | Yes
All Mapped Tax Types | RO-Type 1-Grid |  |  | No | Yes
All Mapped Tax Codes | RO-Type 1-Grid |  |  | No | Yes
All Mapped Pay Codes | RO-Type 1-Grid |  |  | No | Yes
Tax Types (Filter on Tax Type) | RO-Type 1-Grid |  |  | No | Yes
Employee Groups | RO-Type 1-Grid |  |  | No | Yes
Garnishment Groups (Filter on Group Code)-Page | RO-Type 1-Grid |  |  | No | Yes
Disposable Overrides (Filter on Garnishment Group Code)-Page | RO-Type 1-Grid |  |  | No | Yes
Custom Garnishment (Filter on User Tax)-Page | RO-Type 1-Grid |  |  | No | Yes
Companies (Filter on company Code)-Details | RO-Type 1-Grid |  |  | No | Yes
Monthly/Quarterly Tax Type (Filter on Authority Code) | RO-Type 1-Grid |  |  | No | Yes
Custom Taxes (Filter on Tax Code) | RO-Type 1-Grid |  |  | No | Yes
Tax Authprities (Filter on Authority Code) | RO-Type 1-Grid |  |  | No | Yes
Experience Rates | RO-Type 1-Grid |  |  | Yes | Yes
Supplemental Methods | RO-Type 1-Grid |  |  | Yes | Yes
Garnishment Parameters-Fields | RO-Type 1-Grid |  |  | Yes | Yes
Marital Status | RO-Type 1-Grid |  |  | Yes | Yes
Unemployment | RO-Type 1-Grid |  |  | Yes | Yes
Resident / Work Validation | RO-Type 1-Grid |  |  | Yes | Yes
Custom Payments | Type 1-Grid |  |  | Yes | Yes
Custom Tax Codes | Type 1-Grid |  |  | Yes | Yes
Data Sets_Page | Type 1-Grid |  |  | Yes | Yes
Employee Groups_Page | Type 1-Grid |  |  | Yes | Yes
Garnishment Groups-Page | Type 1-Grid |  |  | Yes | Yes
Custom Garnishments-Page | Type 1-Grid |  |  | Yes | Yes
Companies-Page | Type 1-Grid |  |  | Yes | Yes |  |  | 2020-05-03 | 2020-05-03 | 2020-05-10
Address Overrides-Page | Type 1-Grid |  |  | Yes | Yes |  |  | 2020-05-03 | 2020-05-03 | 2020-05-10
Garnishment Formula Overrides-Page | Type 1-Grid |  |  | Yes | Yes |  |  | 2020-05-03 | 2020-05-03 | 2020-05-10
Logins and Permissions-Page | Type 1-Grid |  |  | Yes | Yes |  |  | 2020-05-03 | 2020-05-03 | 2020-05-10
generalConfiguration-Fields |  |  |  |  | Yes |  |  | 2020-05-03 | 2020-05-03 | 2020-05-10
Pension What-If Test-Fields |  |  |  |  | Yes |  |  | 2020-05-03 | 2020-05-03 | 2020-05-10
Pension What-If Test-Page | Type 1-Grid |  |  | Yes | Yes |  |  | 2020-05-03 | 2020-05-03 | 2020-05-10
What-If Test-Page | Type 1-Grid |  |  | Yes | Yes |  |  | 2020-05-03 | 2020-05-03 | 2020-05-10
What-If Test - Tax Details-Fields | Type 1-Grid |  |  | Yes | Yes |  |  | 2020-05-03 | 2020-05-03 | 2020-05-10
What-If Test - Garnishment Details-Fields | Type 1-Grid |  |  | Yes | Yes |  |  | 2020-05-03 | 2020-05-03 | 2020-05-10
What-If Test - Employee Details-Fields |  |  |  |  | Yes |  |  | 2020-05-03 | 2020-05-03 | 2020-05-10
What-If Test - Deductions/Benefit Plans | Type 1-Grid |  |  | Yes | Yes |  |  | 2020-05-03 | 2020-05-03 | 2020-05-10

## TYPE_2
Screen Name | Screen Type | Folder Name (\\ntsrv\Common\Strategic Solutions\Designs & Specs\TF New Arch\Metadata-Mockdata\) | Owner/Creator | Has Filter or CRUD | Metadata Complete? | Mockdata Available? | Tested With Harness | Start Date | Completion Date | Peer Review Complete | Dev Complete | QA Complete
Address Override
Companies | Type2 | Companies | Raji |  | Yes | Yes | Yes | 2020-05-26 | 2020-05-26
Custom Formulas |  | Custom Garnishment Formula | Raji
Custom Garnishment Formulas |  |  |  |  | Yes |  |  | 2020-05-27
Custom Garnishments
Custom Nexus Data
Custom Payments
Custom Payment Exceptions
Custom Tax Payment Overrides
Custom Tax Codes
Dispoasable Overrides
Employee Groups
Garnishment Formula Overrides
Garnishment Groups
Group Overrides
Optional Rate Overrides
Payment Overrides
Reciprocal Overrides
Tax Effective Date Overrides
Unemployment Overrides
Tax Locator