## Metadata
Screen Name | Screen Type | Folder Name (\\ntsrv\Common\Strategic Solutions\Designs & Specs\TF New Arch\Metadata-Mockdata\) | Owner/Creator | Has Filter or CRUD | Metadata Complete? | Mockdata Available? | Tested With Harness | Start Date | Completion Date | Peer Review Complete | Dev Complete | QA Complete
User Data Queries_Tax Authority | RO-Type 1-Grid | RG_Tax Authority | Raji | No | Yes | Yes | Yes | 2020-05-18 | 2020-05-21 | 2020-05-21
User Data Queries_Custom Taxes | RO-Type 1-Grid | RG_Custom Taxes | Raji | No | Yes | Yes | Yes | 2020-05-18 | 2020-05-21 | 2020-05-21
User Data Queries_BSI Taxes | RO-Type 1-Grid | RG_BSI Taxes | Raji | No | Yes | Yes | Yes | 2020-05-18 | 2020-05-21 | 2020-05-21
User Data Queries_Tax Types | RO-Type 1-Grid | RG_Tax Types | Raji | No | Yes | Yes | Yes | 2020-05-18 | 2020-05-21 | 2020-05-21
User Data Queries_Employee Groups | RO-Type 1-Grid | RG_Employee Groups | Raji | No | Yes | Yes | Yes | 2020-05-18 | 2020-05-21 | 2020-05-21
User Data Queries_Garnishment Groups | RO-Type 1-Grid | RG_Garnishment Groups | Raji | No | Yes | Yes | Yes | 2020-05-18 | 2020-05-21 | 2020-05-21
User Data Queries_Disposable Overrides | RO-Type 1-Grid | RG_Disposable Overrides | Raji | No | Yes | Yes | Yes | 2020-05-18 | 2020-05-21 | 2020-05-21
User Data Queries_Custom Garnishments | RO-Type 1-Grid | RG_Custom Garnishments | Raji | No | Yes | Yes | Yes | 2020-05-18 | 2020-05-21 | 2020-05-21
User Data Queries_Garnishment Formula Override | RO-Type 1-Grid | RG_Garnishment Formula Override | Raji | No | Yes | Yes | Yes | 2020-05-18 | 2020-05-21 | 2020-05-21
User Data Queries_All Mapped Tax Types | RO-Type 1-Grid | RG_All Mapped Tax Types | Raji | No | Yes | Yes | Yes | 2020-05-18 | 2020-05-21 | 2020-05-21
User Data Queries_All Mapped Tax User Data Queries_Codes | RO-Type 1-Grid | RG_All Mapped Tax RG_Codes | Raji | No | Yes | Yes | Yes | 2020-05-18 | 2020-05-21 | 2020-05-21
User Data Queries_All Mapped Pay User Data Queries_Codes | RO-Type 1-Grid | RG_All Mapped Pay RG_Codes | Raji | No | Yes | Yes | Yes | 2020-05-18 | 2020-05-21 | 2020-05-21
User Data Queries_Companies | RO-Type 1-Grid | RG_Companies | Raji | No | Yes | Yes | Yes | 2020-05-18 | 2020-05-21 | 2020-05-21
User Data Queries_Experience Rates | RO-Type 1-Grid | RG_ExperienRG_Ce Rates | Vinit | No | Yes | Yes | Yes | 2020-05-18 | 2020-05-21 | 2020-05-21
User Data Queries_Supplemental Methods | RO-Type 1-Grid | RG_Supplemental Methods | Raji | No | Yes | Yes | Yes | 2020-05-18 | 2020-05-21 | 2020-05-21
User Data Queries_Marital Status | RO-Type 1-Grid | RG_Marital Status | Raji | Yes | Yes | Yes | Yes | 2020-05-18 | 2020-05-21 | 2020-05-21
User Data Queries_Resident/Work Validation | RO-Type 1-Grid | RG_Resident/Work Validation | Raji | Yes | Yes | Yes | Yes | 2020-05-18 | 2020-05-21 | 2020-05-21
User Data Queries_Unemployment | RO-Type 1-Grid | RG_Unemployment | Raji | Yes | Yes | Yes | Yes | 2020-05-18 | 2020-05-21 | 2020-05-21
User Data Queries_Populated V3 States | RO-Type 1-Grid | Populated V3 States | Vinit | Yes | Yes | Yes | Yes | 2020-05-18 | 2020-05-21 | 2020-05-22
User Data Queries_Monthly/Quarterly Tax Type | RO-Type 1-Grid | RG_Monthly/Quarterly Tax Type | Raji | Yes | Yes | Yes | Yes | 2020-05-18 | 2020-05-21 | 2020-05-22
User Data Queries_Taxability for Authority | RO-Type 1-Grid | RG_Taxability for Authority | Raji | Yes | Yes | Yes | Yes | 2020-05-18 | 2020-05-21 | 2020-05-21
User Data Queries_Custom Taxability for Authority | RO-Type 1-Grid | RG_Custom Taxability for Authority | Raji | Yes | Yes | Yes | Yes | 2020-05-18 | 2020-05-21 | 2020-05-22
User Data Queries_Custom Overrides for Authority | RO-Type 1-Grid | RG_Custom Overrides for Authority | Raji | Yes | Yes | Yes | Yes | 2020-05-18 | 2020-05-21 | 2020-05-21
User Data Queries_Custom Garnishment Formula | RO-Type 1-Grid | RG_Custom Garnishment Formula | Raji | Yes | Yes | Yes | Yes | 2020-05-18 | 2020-05-21 | 2020-05-21
User Data Queries_All BSI Plans | RO-Type 1-Grid | RG_All BSI Plans | Raji | No | Yes | Yes | Yes | 2020-05-18 | 2020-05-21 | 2020-05-22
User Data Queries_Garnishments Requiring Filing Status | RO-Type 1-Grid | RG_Garnishments Requiring Filing Status | Raji | Yes | Yes | Yes | Yes | 2020-05-18 | 2020-05-21 | 2020-05-22
User Data Queries_Ordered-PerCent Garnishments | RO-Type 1-Grid | RG_Ordered-PerCent Garnishments | Raji | Yes | Yes | Yes | Yes | 2020-05-18 | 2020-05-21 | 2020-05-22
User Data Queries_Valid Tax Formulas | RO-Type 1-Grid | RG_Valid Tax Formulas | Raji | Yes | Yes | Yes | Yes | 2020-05-18 | 2020-05-21 | 2020-05-22
User Data Queries_All Mapped Tax Codes With County | RO-Type 1-Grid | RG_All Mapped Tax Codes With County | Raji | No | Yes | Yes | Yes | 2020-05-18 | 2020-05-21 | 2020-05-22
User Data Queries_Wage Limits By Authority And Tax Type | RO-Type 1-Grid | RG_Wage Limits By Authority And Tax Type | Raji | Yes | Yes | Yes | Yes | 2020-05-18 | 2020-05-21 | 2020-05-21
User Data Queries_Garnishment Disposable Wages | RO-Type 1-Grid | RG_Garnishment Disposable Wages | Raji | Yes | Yes | Yes | Yes | 2020-05-18 | 2020-05-21 | 2020-05-22
User Data Queries_Statement of Exemption Authorities | RO-Type 1-Grid | RG_Statement of Exemption Authorities | Raji | No | Yes | Yes | Yes | 2020-05-18 | 2020-05-21 | 2020-05-22
User Data Queries_Minimum Age Taxes | RO-Type 1-Grid | RG_Minimum Age Taxes | Raji | Yes | Yes | Yes | Yes | 2020-05-18 | 2020-05-21 | 2020-05-22
User Data Queries_Garnishment Parameters | RO-Type 1-Grid | RG_Garnishment Parameters | Raji | Yes | Yes | Yes | Yes | 2020-05-18 | 2020-05-21 | 2020-05-22
Populated V3 States | RO-Type 1-Grid |  |  | No | Yes | Yes | Yes
Address Overrides-Fields | RO-Type 1-Grid |  | Raji | Yes | Yes
Address Overrides-Page | RO-Type 1-Grid |  | Raji | Yes | Yes
All BSI Plans | RO-Type 1-Grid |  |  | No | Yes
All Mapped Tax Codes With County | RO-Type 1-Grid |  |  | No | Yes
Statement of Exemption Authorities | RO-Type 1-Grid |  |  | No | Yes
All Mapped Tax Types | RO-Type 1-Grid |  |  | No | Yes
All Mapped Tax Codes | RO-Type 1-Grid |  |  | No | Yes
All Mapped Pay Codes | RO-Type 1-Grid |  |  | No | Yes
Tax Types (Filter on Tax Type) | RO-Type 1-Grid |  |  | No | Yes
Employee Groups | RO-Type 1-Grid |  |  | No | Yes
Garnishment Groups (Filter on Group Code)-Page | RO-Type 1-Grid |  |  | No | Yes
Disposable Overrides (Filter on Garnishment Group Code)-Page | RO-Type 1-Grid |  |  | No | Yes
Custom Garnishment (Filter on User Tax)-Page | RO-Type 1-Grid |  |  | No | Yes
Companies (Filter on company Code)-Details | RO-Type 1-Grid |  |  | No | Yes
Monthly/Quarterly Tax Type (Filter on Authority Code) | RO-Type 1-Grid |  |  | No | Yes
Custom Taxes (Filter on Tax Code) | RO-Type 1-Grid |  |  | No | Yes
Tax Authprities (Filter on Authority Code) | RO-Type 1-Grid |  |  | No | Yes
Experience Rates | RO-Type 1-Grid |  |  | Yes | Yes
Supplemental Methods | RO-Type 1-Grid |  |  | Yes | Yes
Garnishment Parameters-Fields | RO-Type 1-Grid |  |  | Yes | Yes
Marital Status | RO-Type 1-Grid |  |  | Yes | Yes
Unemployment | RO-Type 1-Grid |  |  | Yes | Yes
Resident / Work Validation | RO-Type 1-Grid |  |  | Yes | Yes
Custom Payments | Type 1-Grid |  |  | Yes | Yes
Custom Tax Codes | Type 1-Grid |  |  | Yes | Yes
Data Sets_Page | Type 1-Grid |  |  | Yes | Yes
Employee Groups_Page | Type 1-Grid |  |  | Yes | Yes
Garnishment Groups-Page | Type 1-Grid |  |  | Yes | Yes
Custom Garnishments-Page | Type 1-Grid |  |  | Yes | Yes
Companies-Page | Type 1-Grid |  |  | Yes | Yes |  |  | 2020-05-03 | 2020-05-03 | 2020-05-10
Address Overrides-Page | Type 1-Grid |  |  | Yes | Yes |  |  | 2020-05-03 | 2020-05-03 | 2020-05-10
Garnishment Formula Overrides-Page | Type 1-Grid |  |  | Yes | Yes |  |  | 2020-05-03 | 2020-05-03 | 2020-05-10
Logins and Permissions-Page | Type 1-Grid |  |  | Yes | Yes |  |  | 2020-05-03 | 2020-05-03 | 2020-05-10
generalConfiguration-Fields |  |  |  |  | Yes |  |  | 2020-05-03 | 2020-05-03 | 2020-05-10
Pension What-If Test-Fields |  |  |  |  | Yes |  |  | 2020-05-03 | 2020-05-03 | 2020-05-10
Pension What-If Test-Page | Type 1-Grid |  |  | Yes | Yes |  |  | 2020-05-03 | 2020-05-03 | 2020-05-10
What-If Test-Page | Type 1-Grid |  |  | Yes | Yes |  |  | 2020-05-03 | 2020-05-03 | 2020-05-10
What-If Test - Tax Details-Fields | Type 1-Grid |  |  | Yes | Yes |  |  | 2020-05-03 | 2020-05-03 | 2020-05-10
What-If Test - Garnishment Details-Fields | Type 1-Grid |  |  | Yes | Yes |  |  | 2020-05-03 | 2020-05-03 | 2020-05-10
What-If Test - Employee Details-Fields |  |  |  |  | Yes |  |  | 2020-05-03 | 2020-05-03 | 2020-05-10
What-If Test - Deductions/Benefit Plans | Type 1-Grid |  |  | Yes | Yes |  |  | 2020-05-03 | 2020-05-03 | 2020-05-10