## Metadata
Screen Name | Screen Type | Folder Name | Owner/Creator | Has Filter or CRUD | Metadata Complete? | Mockdata Available? | Tested With Harness | Start Date | Completion Date | Peer Review Complete | Dev Complete | QA Complete
Populated V3 States | RO-Type 1-Grid | PopulatedV3States | Jeff | No | Yes | Yes | No
All BSI Plans | RO-Type 1-Grid | AllBSIPlans | Jeff | No | Yes | Yes | Yes |  | 2020-05-20
All Mapped Tax Codes With County | RO-Type 1-Grid | AllMappedTaxCodesWithCounty | Jeff | No | Yes | Yes | Yes |  | 2020-05-20
Statement of Exemption Authorities | RO-Type 1-Grid | StatementOfExemptionAuthorities | Jeff | No | Yes | Yes | Yes |  | 2020-05-20
All Mapped Tax Types | RO-Type 1-Grid | AllMappedTaxCodesWithCounty | Jeff | No | Yes | Yes | Yes |  | 2020-05-21
All Mapped Tax Codes | RO-Type 1-Grid | AllMappedTaxCodesWithCounty | Jeff | No | yes | Yes | Yes |  | 2020-05-21
All Mapped Pay Codes | RO-Type 1-Grid | AllMappedTPayCodes | Jeff | No | Yes | Yes | Yes |  | 2020-05-21
Custom Garnishment Formula-Fields
Custom Garnishment Formula-Page | RO-Type 1-Grid | CustomGarnishmentFormula | Jeff | No | Yes | Yes | Yes |  | 2020-05-21
Tax Types (Filter on Tax Type) | RO-Type 1-Grid | TaxTypes | Jeff | No | Yes | Yes | Yes |  | 2020-05-20
Employee Groups (Filter on Group Code)-Fields
Employee Groups (Filter on Group Code)-Page | RO-Type 1-Grid |  |  | No
Garnishment Groups (Filter on Group Code)-Fields
Garnishment Groups (Filter on Group Code)-Page | RO-Type 1-Grid | GarnishmentGroups |  | No
Disposable Overrides (Filter on Garnishment Group Code)_Fields
Disposable Overrides (Filter on Garnishment Group Code)-Page | RO-Type 1-Grid |  |  | No
Custom Garnishment (Filter on User Tax)-Fields
Custom Garnishment (Filter on User Tax)-Page | RO-Type 1-Grid |  |  | No
Companies (Filter on company Code)-Details | RO-Type 1-Grid | Companies | Jeff | No | Yes | Yes | No
Companies (Filter on company Code)-Page
Monthly/Quarterly Tax Type (Filter on Authority Code) | RO-Type 1-Grid | CustomTaxes | Jeff | No | Yes | Yes | No
Custom Taxes (Filter on Tax Code) | RO-Type 1-Grid |  |  | No
Tax Authprities (Filter on Authority Code) | RO-Type 1-Grid |  |  | No
Experience Rates | RO-Type 1-Grid |  |  | Yes
Supplemental Methods | RO-Type 1-Grid | SupplementalMethods | Jeff | Yes | Yes | Yes | No
Garnishment Parameters-Fields | RO-Type 1-Grid |  |  | Yes |  |  |  | 2020-05-03 | 2020-05-03
Garnishment Parameters-Page | [7 empty] | 2020-05-03 | 2020-05-03
Marital Status | RO-Type 1-Grid | MaritalStatus | Jeff | Yes | Yes | Yes | No | 2020-05-03 | 2020-05-03
Unemployment | RO-Type 1-Grid | Unemployment | Jeff | Yes | Yes | Yes | No | 2020-05-03 | 2020-05-03
Resident / Work Validation | RO-Type 1-Grid |  |  | Yes |  |  |  | 2020-05-03 | 2020-05-03
Custom Payments | Type 1-Grid | CustomPayments | Jeff | Yes | Yes | Yes | No | 2020-05-03 | 2020-05-03
Custom Tax Codes | Type 1-Grid | CustomTaxCodes | Jeff | Yes | Yes | Yes | No | 2020-05-03 | 2020-05-03
Data Sets_Field | [7 empty] | 2020-05-03 | 2020-05-03
Data Sets_Page | Type 1-Grid |  |  | Yes |  |  |  | 2020-05-03 | 2020-05-03
Employee Groups_Fields | [7 empty] | 2020-05-03 | 2020-05-03
Employee Groups_Page | Type 1-Grid |  |  | Yes |  |  |  | 2020-05-03 | 2020-05-03
Garnishment Groups-Fields | [7 empty] | 2020-05-03 | 2020-05-03
Garnishment Groups-Page | Type 1-Grid |  |  | Yes |  |  |  | 2020-05-03 | 2020-05-03
Custom Garnishments-Fields | [7 empty] | 2020-05-03 | 2020-05-03
Custom Garnishments-Page | Type 1-Grid |  |  | Yes |  |  |  | 2020-05-03 | 2020-05-03
Companies-Fields | [7 empty] | 2020-05-03 | 2020-05-03
Companies-Page | Type 1-Grid | Companies | Jeff | Yes | Yes | Yes | No | 2020-05-03 | 2020-05-03
Address Overrides-Fields | [7 empty] | 2020-05-03 | 2020-05-03
Address Overrides-Page | Type 1-Grid |  |  | Yes |  |  |  | 2020-05-03 | 2020-05-03
Garnishment Formula Overrides-Fields | [7 empty] | 2020-05-03 | 2020-05-03
Garnishment Formula Overrides-Page | Type 1-Grid |  |  | Yes |  |  |  | 2020-05-03 | 2020-05-03
Logins and Permissions-Fields | [7 empty] | 2020-05-03 | 2020-05-03
Logins and Permissions-Page | Type 1-Grid |  |  | Yes |  |  |  | 2020-05-03 | 2020-05-03
generalConfiguration-Fields | [7 empty] | 2020-05-03 | 2020-05-03
Pension What-If Test-Fields | [7 empty] | 2020-05-03 | 2020-05-03 | 2020-05-10
Pension What-If Test-Page | Type 1-Grid |  |  | Yes |  |  |  | 2020-05-03 | 2020-05-03 | 2020-05-10
What-If Test-Page | Type 1-Grid |  |  | Yes |  |  |  | 2020-05-03 | 2020-05-03 | 2020-05-10
What-If Test - Tax Details-Fields | Type 1-Grid |  |  | Yes |  |  |  | 2020-05-03 | 2020-05-03 | 2020-05-10
What-If Test - Garnishment Details-Fields | Type 1-Grid |  |  | Yes |  |  |  | 2020-05-03 | 2020-05-03 | 2020-05-10
What-If Test - Employee Details-Fields | [7 empty] | 2020-05-03 | 2020-05-03 | 2020-05-10
What-If Test - Deductions/Benefit Plans | Type 1-Grid |  |  | Yes |  |  |  | 2020-05-03 | 2020-05-03 | 2020-05-10
User Data Queries_Granishment Parameters | RO-Type 1-Grid | GarnishmentParaments | Jeff | No | Yes | Yes | No | 2020-05-03 | 2020-05-03 | 2020-05-10
User Data Queries_minimumAgeTaxes | RO-Type 1-Grid | MinimumAgeTaxes | Jeff | No | Yes | Yes | No | 2020-05-03 | 2020-05-03 | 2020-05-10
User Data Querirs_statementOfExemptionAuthorities | RO-Type 1-Grid | StatementOfExemptionAuthorities | Jeff | No | Yes | Yes | yes | 2020-05-03 | 2020-05-20 | 2020-05-10
User Data Queries_Garnishment Disposable Wages | RO-Type 1-Grid |  |  | No |  |  |  | 2020-05-03 | 2020-05-03 | 2020-05-10
User Data Queries_Wage Limits By Authority And Tax Type | RO-Type 1-Grid |  |  | No |  |  |  | 2020-05-03 | 2020-05-03 | 2020-05-10
User Data Queries_Taxability for Authority | RO-Type 1-Grid | TaxabilityForAuthorityAndTaxType | Jeff | No | Yes | Yes | No | 2020-05-03 | 2020-05-03 | 2020-05-10
User Data Queries_Custom Taxability for Authority | RO-Type 1-Grid | CustomTaxiabilityforAuthority | Jeff | No | Yes | Yes | No | 2020-05-03 | 2020-05-03 | 2020-05-10
User Data Queries_Custom Overrides for Authority | RO-Type 1-Grid | CustomOverridesforAuthority | Jeff | No | Yes | Yes | No | 2020-05-03 | 2020-05-03 | 2020-05-10
User Data Queries_Custom Garnishment Formula | RO-Type 1-Grid | CustomGarnishmentFormula | Jeff | No | Yes | Yes | No | 2020-05-03 | 2020-05-03 | 2020-05-10
User Data Queries_All BSI Plans | RO-Type 1-Grid | AllBSIPlans | Jeff | No | Yes | Yes | No | 2020-05-03 | 2020-05-03 | 2020-05-10
User Data Queries_Garnishments Requiring Filing Status | RO-Type 1-Grid |  |  | No |  |  |  | 2020-05-03 | 2020-05-03 | 2020-05-10
User Data Queries_Ordered-Percent Garnishments | RO-Type 1-Grid |  |  | No |  |  |  | 2020-05-03 | 2020-05-03 | 2020-05-10
User Data Queries_Valid Tax Formulas | RO-Type 1-Grid |  |  | No |  |  |  | 2020-05-03 | 2020-05-03 | 2020-05-10
User Data Queries_All Mapped Tax Codes With County | RO-Type 1-Grid |  |  | No |  |  |  | 2020-05-03 | 2020-05-03 | 2020-05-10
User Data Queries-monthly_Quarterly Tax Type | RO-Type 1-Grid |  |  | No |  |  |  | 2020-05-03 | 2020-05-03 | 2020-05-10