## Sheet1
| Status | Done | Not Done
| UI/Screen | UI Development/Metadata | APIs Development | UI-API Integration | QA Complete
UDQ | Taxability for Authority | Done | Done | Done | Done |  | Completed | Not Completed
| Companies | Done | Done | Done | Not Done | UI Development/Metadata | 54 | 30
| Garnishment Disposable Wages | Done | In Progress | In Progress | Not Done | API Development | 32 | 48
| Ordered-Percent Garnishments | Done | Done | In Progress | Done | UI-API Integration | 27 | 52
| Unemployment | Done | Done | Done | Not Done | QA Complete | 20 | 65
| Minimum Age Taxes | Done | Done | Done | Done
| Custom Taxability for Authority | Done | Done | Done | Done
| Wage Limits By Authority And Tax Type | Done | Done | Done | Done
| Garnishment Parameters | Done | Done | Done | Done
| Statement of Exemption Authorities | Done | Done | Done | Done
| All Mapped Tax Codes With County | Done | Done | Done | Done
| Valid Tax Formulas | Done | Done | Done | Not Done
| Garnishments Requiring Filing Status | Done | Done | Done | Done
| BSI Taxes | Done | Done | Done | Done
| Monthly/Quarterly Tax Type | Done | Done | Done | Done
| Tax Authority | Done | Done | Done | Done
| All BSI Plans | Done | Done | Done | Not Done
| All Mapped Pay Codes | Done | Done | Done | Done
| All Mapped Tax Codes | Done | Done | Done | Done
| All Mapped Tax Types | Done | Done | Done | Done
| Experience Rates | Done | Done | Done | Not Done
| Populated V3 States | Done | Done | Done | Done
| Custom Taxes | Done | Done | Done | Done
| Disposable Overrides | Done | Done | Done | Done
| Garnishment Groups | Done | Done | Done | Done
| Tax Types | Done | Done | Done | Done
| Garnishment Formula Override | In Progress | Not Done | Not Done | Not Done
| Custom Garnishments | Done | Done | Done | Not Done
| Marital Status | Done | In Progress | In Progress | Not Done
| Resident/Work Validation | Done | In Progress | In Progress | Not Done
| Supplemental Methods | Done | In Progress | In Progress | Not Done
| Custom Overrides for Authority | Done | Done | Done | Not Done
| Custom Garnishment Formula | Done | In Progress | In Progress | Not Done
| Employee Groups | Done | Done | Done | Not Done
Type1 | Custom Payments | Done | Done | Not Done | Not Done
| Custom Tax Codes | Done | Done | Not Done | Not Done
| Data Sets | Not Done | Not Done | Not Done | Not Done
| Employee Groups | Done | Not Done | Not Done | Not Done
| Garnishment Groups | Done | Not Done | Not Done | Not Done
| Custom Garnishment | Done | Done | Not Done | Not Done
| Companies | Done | Done | Not Done | Not Done
| Address Overrides | Done | Not Done | Not Done | Not Done
| Garnishment Formula Overrides | Not Done | Not Done | Not Done | Not Done
| Logins and Pemissions | Done | Not Done | Not Done | Not Done
| Pension What-If Test | Not Done | Not Done | Not Done | Not Done
| What If Test | Not Done | Not Done | Not Done | Not Done
| What If Test -Tax Details | Not Done | Not Done | Not Done | Not Done
| What If Test - Garnishment Details | Not Done | Not Done | Not Done | Not Done
| What If Test - Deductions/Benefit Plans | Not Done | Not Done | Not Done | Not Done
Type2 | Custom Formulas | Done | Not Done | Not Done | Not Done
| Worksites | Done | Not Done | Not Done | Not Done
| Unemployment Overrides | Done | Not Done | Not Done | Not Done
| Payment Overrides | Done | Not Done | Not Done | Not Done
| Reciprocal Overrides | Done | Not Done | Not Done | Not Done
| Optional Rate Overrides | Done | Not Done | Not Done | Not Done
| Diposable Overrides | Done | Not Done | Not Done | Not Done
| Custom Tax Payment Overrides | Done | Not Done | Not Done | Not Done
| Custom Payment Exceptions | Done | Not Done | Not Done | Not Done
| Custom Nexus Data | Done | Not Done | Not Done | Not Done
| Custom Garnishment Formulas | Done | Not Done | Not Done | Not Done
Type3 | Map Payment Codes | Not Done | Not Done | Not Done | Not Done
| Max Tax Type | Not Done | Not Done | Not Done | Not Done
| Message Viewer | Done | Not Done | Not Done | Not Done
| PA Services Tax Report | Done | Not Done | Not Done | Not Done
| Audit Log Viewer | Not Done | Not Done | Not Done | Not Done
Type4 | Tax History Report | Not Done | Not Done | Not Done | Not Done
Cruds | Marital Status Report (File Generation) | Not Done | Not Done | Not Done | Not Done
| Batch Test | Not Done | Not Done | Not Done | Not Done
| Permissions | Not Done | Not Done | Not Done | Not Done
| Custom Backup/Restore (File Generation/Restore) | Not Done | Not Done | Not Done | Not Done
| Message To Supress (Related to Message Viewer) | Not Done | Not Done | Not Done | Not Done
| Any View Output Required (View File, View PDF etc.) | Not Done | Not Done | Not Done | Not Done
Pages with Links | Custom Payments Code Usage | Not Done | Not Done | Not Done | Not Done
| Mapping Tools | Not Done | Not Done | Not Done | Not Done
| Tax Code Usage Summary | Not Done | Not Done | Not Done | Not Done
| Custom Tax Type Usage | Not Done | Not Done | Not Done | Not Done
| Report Tools | Not Done | Not Done | Not Done | Not Done
| User Data Queries | Not Done | Not Done | Not Done | Not Done
| System Tools | Not Done | Not Done | Not Done | Not Done
External Link Areas | Cyclic Bulletin | Not Done | Not Done | Not Done | Not Done
| Locator Bulletins | Not Done | Not Done | Not Done | Not Done
| Regulatory Bulletins | Not Done | Not Done | Not Done | Not Done
| U.S. QuickFormulas | Not Done | Not Done | Not Done | Not Done
| U.S. Pension QuickFormulas | Not Done | Not Done | Not Done | Not Done
| U.S. WageAttachment QuickFormulas | Not Done | Not Done | Not Done | Not Done
Note on B76: Vinit Naik: May Require Common Components